## Sheet1
ID | Area | Scenario | Pre-reqs | Steps | Expected | Priority | Owner | Status
MP-001 | App Boot | App loads without console errors | Deployed build on Vercel (prod) | Open https://www.e-ctrl.ai ; check browser console | No uncaught errors; main hero and CTA render within 2s on desktop broadband | P0
MP-002 | Routing | All primary routes resolve (/, /audit, /privacy, /terms) | Prod build | Navigate to each route via nav and direct URL | 200 OK; correct content; no hydration mismatch | P0
MP-003 | Responsive | Mobile layout integrity | Prod build | Open on iPhone 14/Pixel 7 viewports | Hero, CTAs, forms, and footer do not overflow; tap targets ≥ 44px; no horizontal scroll | P0
MP-010 | Auth | Email sign-in/up flow works | Valid test user | Sign up, verify email if required, sign in, sign out | User session persists; secure cookies; redirects correct | P0
MP-011 | Roles | Admin vs User permissions enforced | Admin and regular accounts | Access /admin with both accounts | Admin sees dashboard; user is blocked or redirected | P0
MP-020 | Seller Type | New vs Existing seller branching | Auth optional | Select 'New Seller' vs 'Existing Seller' in intake | Form questions and copy adapt to selection | P0
MP-021 | Seller Type | Type-safe handling of data models | Valid input | Submit forms for both types | No TS runtime errors; correct analyzer called per type | P0
MP-030 | Form | Client intake validates required fields | Prod build | Attempt submit with empty required fields | Inline validation messages; submit disabled until valid | P0
MP-031 | Form | File/link inputs sanitize & validate (ASIN/Storefront URL) | Test URLs/ASINs | Enter malformed and valid values | Malformed blocked with helpful error; valid accepted | P0
MP-032 | Form | Rate-limit & debounce on API calls | Dev tools | Spam submit or field that triggers API | Server returns 429 only when truly exceeded; UI graceful | P0
MP-040 | Scraper | ASIN/Storefront scrape succeeds and times out gracefully | Test ASIN(s) & storefront | Run audit with known valid and invalid inputs | Valid returns structured data; invalid returns friendly message; no crash | P0
MP-041 | Data Mapping | Scraped fields map to internal schema | Known fixture | Compare raw -> normalized objects | All required fields populated or safely defaulted | P0
MP-050 | IDQ Engine | Binary metric computation correct | Fixture inputs for pass/fail | Run engine over fixtures | Each metric boolean matches spec; totals correct | P0
MP-051 | IDQ Engine | New vs Existing seller recommendations diverge | Two fixtures (new/existing) | Generate outputs for both | Existing: improvement roadmap; New: preview listing plan | P0
MP-060 | PDF | PDF generation completes under 10s | Queue/service running | Trigger audit; wait for PDF | Downloadable PDF renders all sections, logos, charts | P0
MP-061 | Email | Resend/Postmark email delivery & DKIM alignment | Transactional template & domain DKIM set | Send to test inboxes (Gmail/Outlook) | Delivered to Inbox (not spam); from domain aligned; links trackable | P0
MP-070 | DB | Supabase writes with RLS policies | Auth tokens | Create/read/update user-owned records | User sees only their records; RLS blocks cross-tenant access | P0
MP-071 | Storage | Uploaded assets stored & access-controlled | Storage bucket | Upload, fetch via signed URL | Public assets as intended; private require signed URL; expiry works | P0
MP-080 | Admin | Admin dashboard metrics accurate | Seeded data | Compare metrics to DB queries | Counts (audits, users, success rate) match | P0
MP-081 | Analytics | Event tracking fires once per action | Analytics enabled | Trigger CTA, form submit, PDF download | One event each; correct props (sellerType, idqScore, plan) | P0
MP-090 | Performance | Core Web Vitals budget | Lighthouse | Run Lighthouse on mobile | LCP < 3.0s, CLS < 0.1, INP < 200ms | P0
MP-091 | SEO | Meta tags, OG, schema present | Prod URL | View source / use validator | Title/desc, OG image, JSON-LD Product/Software schema valid | P0
MP-092 | Accessibility | Keyboard nav & landmarks | Prod build | Tab through UI; check aria labels | Focusable order logical; contrast meets WCAG AA; skip link exists | P0
MP-100 | Errors | Global error boundary renders fallback | Force error | Simulate throw in component | Friendly fallback UI; error logged (Sentry/console) | P0
MP-101 | Retry/Queue | Background job retries with backoff | Queue worker | Force transient failure in PDF/scrape | Automatic retries; final failure notifies user | P0
MP-102 | Rate Limits | API protection | Edge functions | Exceed per-IP limit | Graceful 429 with wait messaging; no crash | P0
MP-110 | Security | Secrets not exposed client-side | Inspect bundles | Search build for API keys | No secrets in client JS; env vars server-only | P0
MP-111 | Security | CORS & headers set | Prod build | Inspect response headers | CSP, HSTS, X-Frame-Options, Referrer-Policy present & correct | P0